## Sheet1
Notulen Meeting QCC
29 Juli 2026
| Peserta Meeting : |  | Yanuar
Mitra
Mitha
Depta
Khabib
Brainstorming
Pekerjaan Rutin:
| 1 | Closing HS
| 2 | Request Peta
| 3 | Cek BAPP Kemitraan
| 4 | Update Geodatabase
| 5 | Update Koordinat TPH
| 6 | Create Block SAP
| 7 | Rekap Data Replanting
| 8 | Rekap Data Cuci Parit
| 9 | Monitoring Patok HGU
| 10 | Desktop Study
| Step 1 |  | Latar Belakang
| No | Dept | KPI ytd Juni 2026 | Target | Aktual | %
| 1 | GIS | Enterprise GIS Development |  |  | 0%
| 2 | RS | Provide Aerial Survey (Exclude Kalteng) | 16 | 7 | 43.75%
| 3 | RS | Image processing (HO) | 16 | 11 | 68.75%
| 4 | SA | Mapping Area 3rd Party Supplier TBS (NPN, EBL, GBSM, BBB) | 45 | 34.4 | 76.44%
| 5 | SA | Leaf Nutrient Prediction Using Remote Sensing (K) - Busang & SLE | 90 | 70 | 77.78%
| 6 | GIS | Production Line: TPH Inventory and verification | 50 | 41.55 | 83.1%
| 7 | SUR | Improvement Profile | 8 | 7 | 87.5%
| 8 | GIS | Plantation Progress Monitoring | 100 | 91 | 91%
| 9 | GIS | Replanting design Implementation & Monitoring (EBL, DLJ, FLTI) | 60 | 55 | 91.67%
| 10 | GIS | Drainage Network Sanitation and Flow Engineering | 75 | 70 | 93.33%
| 11 | SA | Dantotsu Water Management (EBL) | 60 | 59 | 98.33%
| 12 | RS | Digital Terrain Model (DTM) Generation | 4 | 4 | 100%
Enterprise GIS Development
Ultimate Goals
1 | Higest Yield CPO |  | 2 aspek ini yang terkait
2 | Eficiency cost
3 | Sustainability Growth
|  |  | 5C | Aspek Operasional | Data Estimasi | Dampak Biaya
Consumer
Competitor
Climate Business Change
Company
Colaborator
|  |  | SWOT | TOWS
RINCIAN ENTERPRISE GIS
Kelompok Kegiatan |  |  | Rincian Aktivitas | Progress %
1. Perencanaan |  |  | Analisis kebutuhan bisnis, identifikasi stakeholder, penyusunan roadmap Enterprise GIS, penyusunan standar data spasial | 100
2. Infrastruktur |  |  | Pengadaan server GIS, instalasi database, konfigurasi web server, storage, backup, disaster recovery | 60
3. Database Spasial |  |  | Desain geodatabase, pembuatan schema, domain, subtype, relationship class, versioning, indexing | 14.2857
4. Integrasi Data |  |  | Import SHP, Excel, GPS, Drone, ERP, IoT, sensor lapangan | 28.5714
5. Akuisisi Data |  |  | Survey GPS, Drone Mapping, Mobile GIS, digitasi, validasi lapangan | 100
6. Pengelolaan Data |  |  | Editing, QC/QA, topology checking, metadata, update data berkala | 20
7. Analisis Spasial |  |  | Overlay, buffer, suitability analysis, network analysis, deforestation analysis, hotspot, change detection | 100
8. WebGIS |  |  | Pengembangan portal GIS, dashboard, web map, layer service, feature service | 80
9. Mobile GIS |  |  | Form survey, offline map, sinkronisasi data lapangan, tracking petugas | 75
10. Otomasi |  |  | Python scripting, ETL, scheduled process, batch processing, report otomatis | 60
11. Dashboard & Reporting |  |  | Dashboard operasional, KPI spasial, monitoring progres, executive dashboard | 0
12. Keamanan |  |  | Hak akses user, role management, audit log, enkripsi, authentication
13. Integrasi Sistem |  |  | Integrasi ERP, HR, Asset Management, SAP, EUDR, RSPO, Power BI
14. Pelatihan |  |  | Training admin GIS, operator GIS, user bisnis
15. Operasional |  |  | Monitoring server, maintenance, update software, troubleshooting, helpdesk
16. Pengembangan |  |  | Pengembangan aplikasi GIS baru sesuai kebutuhan bisnis
GENBA
|  | 1 | Checklist kelengkapan dan kesesuaian Geodatabase All Estate
2